## Estimates
Module | Task | Effort (In Man days) | Resource
Backend Activities
Database Design
| Designing the collections structure | 3
Super Admin Module |  |  | R1
| Defining the collection structures for - Organizations, Applications, LicenseTypes, Licences | 1
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 2
Admin Module |  |  | R1
| Defining the collection structures for - Roles,Users,UserTypes, FunctionalArea, UserApplicationAccess | 1
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 2
Customer Management |  |  | R1
| Defining the collection structures for - Customers,CustomerNVendorTypes,Attachments/Documents | 1
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 2
| Bulk upload functionality implementation for customer creation | 2
Vendor Management |  |  | R1
| Defining the collection structures for - Vendors,Attachments/Documents | 0.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 1.5
| Bulk upload functionality implementation for vendor creation | 2
Forms |  |  | R2
| Defining the collection structures for - Forms, FormTypes | 0.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 0.5
Program Management |  |  | R2
| Defining the collection structures for - Programs, ProgramTypes, Projects, ProjectTeamMembers, CSFs, DCLs, Milestones, DEN, Attachments/Documents | 1.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 2
| Bulk upload functionality implementation for Program creation and setup | 2
| Email functionality in following cases: - Program/Project/CSF/Milestone end date in a week to end date - Program/Project/CSF/Milestone delayed - User is added to a new project | 2
Organization Chart |  |  | R2
| REST API definition for - GET organization chart at project level | 1
RACI |  |  | R2
| Defining the collection structures for - CSFRs, PPRs | 0.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 0.5
Reporting |  |  | R2
| REST API Definition for - GET • Reporting KPIs i. Total Programs ii. Total Projects iii. Total CSFs iv. No of projects by status v. No of Projects received/created by month for last 1 year All the above KPIs with the filtering capability on Status (Project and Program) and Program. | 4
Planning Calendar |  |  | R2
| Defining the collection structures for - Appointments | 0.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 0.5
Glossaries |  |  | R2
| Defining the collection structures for - Glossaries | 0.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 0.5
Help |  |  | R2
| Defining the collection structures for - Topics, FAQs | 0.5
| Exposing collections as REST APIs - GET with filters - POST - PUT - DELETE | 0.5
Page Clock |  |  | R2
| REST API Definition for - GET all program/project/CSF/DCL/Milestone due dates | 1
Workflow Management |  |  | R1 & R2
| User Creation | 1.5
| Program Creation | 1.5
| Project Creation | 1.5
| Team Member addition to project | 1.5
| Document creation | 1.5
UI Activities
Super Admin Module |  |  | R3
| Service Integration | 1.5
| Unit Testing | 0.5
Admin Module |  |  | R3
| Service Integration | 1.5
| Unit Testing | 0.5
Customer Management |  |  | R3
| Service Integration | 3
| Unit Testing | 1
Vendor Management |  |  | R3
| Service Integration | 3
| Unit Testing | 1
Forms |  |  | R3
| Service Integration | 1.5
| Unit Testing | 0.5
Program Management |  |  | R4
| Service Integration | 4
| Unit Testing | 1
Organization Chart |  |  | R4
| Service Integration | 1.5
| Unit Testing | 0.5
RACI |  |  | R4
| Service Integration | 1.5
| Unit Testing | 0.5
Reporting |  |  | R4
| Service Integration | 3
| Unit Testing | 1
Planning Calendar |  |  | R4
| Service Integration | 2
| Unit Testing | 1
Glossaries |  |  | R4
| Service Integration | 2
| Unit Testing | 1
Help |  |  | R4
| Service Integration | 1
| Unit Testing | 0.5
Page Clock |  |  | R4
| Service Integration | 1
| Unit Testing | 0.5
Workflow Management
| Service Integration | 4
| Unit Testing | 2
Testing
Integration Testing |  | 2
Functionality Testing |  | 2
Deployement
Application Deployment and Hypercare |  | 3
Total |  | 93

## Timeline
| W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4 |  |  |  |  | W5 |  |  |  |  | W6 |  |  |  |  | W7
Modules | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35
Backend Activities
Database Design | R1&R2
Super Admin Module |  |  |  | R1
Admin Module | [6 empty] | R1
Customer Management | [9 empty] | R1 | [25 empty] | R1 | Backend Developer
Vendor Management | [14 empty] | R1 | [20 empty] | R2 | Backend Developer
Forms | [18 empty] | R1 | [16 empty] | R3 | Frontend Developer
Program Management |  |  |  | R2 | [31 empty] | R4 | Frontend Developer
Organization Chart | [11 empty] | R2
RACI | [12 empty] | R2
Reporting | [13 empty] | R2
Planning Calendar | [17 empty] | R2
Glossaries | [18 empty] | R2
Help | [19 empty] | R2
Page Clock | [20 empty] | R2
Workflow Management | [19 empty] | R1 & R2
UI Activities
Super Admin Module | [6 empty] | R3
Admin Module | [9 empty] | R3
Customer Management | [14 empty] | R3
Vendor Management | [18 empty] | R3
Forms | [22 empty] | R3
Program Management | [8 empty] | R4
Organization Chart | [12 empty] | R4
RACI | [14 empty] | R4
Reporting | [16 empty] | R4
Planning Calendar | [20 empty] | R4
Glossaries | [23 empty] | R4
Help | [23 empty] | R3
Page Clock | [25 empty] | R4
Workflow Management | [26 empty] | R3 & R4
Testing
Integration Testing | [30 empty] | R1,2,3&4
Functionality Testing
Deployment
Application Deployment and Hypercare | [32 empty] | R1,2,3&4