## Sheet1
Module | Task | Responsible | Start Date | End Date | Status
Super Admin Module |  |  |  |  | Completed
| Service Integration | Sohail | 2023-02-09 | 2023-02-10
| Unit Testing | Sohail | 2023-02-10 | 2023-02-10
Admin Module |  |  |  |  | Completed
| Service Integration | Sohail | 2023-02-13 | 2023-02-14
| Unit Testing | Sohail | 2023-02-14 | 2023-02-14
Customer Management |  |  |  |  | Completed | Attachment is pending
| Service Integration | Sohail | 2023-02-03 | 2023-02-07
| Unit Testing | Sohail | 2023-02-08 | 2023-02-08
Vendor Management |  |  |  |  | Completed | Attachment is pending
| Service Integration | Sohail | 2023-02-15 | 2023-02-17
| Unit Testing | Sohail | 2023-02-20 | 2023-02-20
Forms |  |  |  |  | In progress
| Service Integration | Sohail | 2023-02-21 | 2023-02-21
| Unit Testing | Sohail | 2023-02-23 | 2023-02-23
Program Management |  |  |  |  | Completed | Attachment is pending
| Service Integration | Sohail | 2023-02-24 | 2023-03-03
| Unit Testing | Sohail | 2023-03-06 | 2023-03-07
Organization Chart |  |  |  |  | Completed
| Service Integration | Sohail | 2023-03-28 | 2023-03-29
| Unit Testing | Sohail | 2023-03-30 | 2023-03-30
RACI |  |  |  |  | In progress
| Service Integration | Sohail | 2023-03-31 | 2023-04-03
| Unit Testing | Sohail | 2023-04-04 | 2023-04-04
Reporting |  |  |  |  | Completed
| Service Integration | Sohail | 2023-04-05 | 2023-04-10
| Unit Testing | Sohail | 2023-04-11 | 2023-04-11
Planning Calendar |  |  |  |  | In Progress
| Service Integration | Sohail | 2023-04-12 | 2023-04-13
| Unit Testing | Sohail | 2023-04-14 | 2023-04-14
Glossaries |  |  |  |  | Completed
| Service Integration | Sohail | 2023-03-28 | 2023-03-29
| Unit Testing | Sohail | 2023-03-30 | 2023-03-30
Help |  |  |  |  | Completed
| Service Integration | Sohail | 2023-04-17 | 2023-04-18
| Unit Testing | Sohail | 2023-04-19 | 2023-04-19
Page Clock |  |  |  |  | Open
| Service Integration | Sohail | 2023-04-20 | 2023-04-20
| Unit Testing | Sohail | 2023-04-21 | 2023-04-21
Bulk Upload Functionality |  |  |  |  | Open
| Service Integration | Sohail | 2023-04-24 | 2023-04-26
| Unit Testing | Sohail | 2023-04-27 | 2023-04-28
Testing
Integration Testing |  | Sohail | 2023-05-02 | 2023-05-04
Functionality Testing |  | Sohail | 2023-05-05 | 2023-05-11
Deployement
Application Deployment and Hypercare |  | Sohail | 2023-05-12 | 2023-05-16